## Sheet1
Week | Front end | Back end
2023-02-01 | Add Flask code | Create project
2023-02-07 | Add home page | Create github action
2023-02-14 | add page for send data to model | Add function for sklearn model
2023-02-21 | get api response from function | Add Makefile for test and check code
2023-02-28 | Add test for frontend | Add test for APIs
2023-03-07 | demo frontend functionlaity | demo rest api calls
2023-03-14 | final changes in frontend | clean up code
2023-03-21 | final demo | final demo